## Instructions
Epic Name
COLUMN | DESCRPTION
Id of the Test Case (US-SC-TC) | Identifier of the test case composed of 3 elements: US: number of the user story; SC: scenario number within the user story; TC: number of the test case associated with the scenario. (Example: for User Story 1 with 5 scenarios and several test cases for the same scenario, the Id of the second scenario and the third associated test case would be 01-02-03)
User Story Name | Name of the User Story
Scenario | Drop-down list of the possible scenarios to be associated with the User Story.
Preconditions | Conditions that must be fulfilled before runing the test
Test Case Description | Detailed description of the test associated with the selected scenario
Acceptance Criteria | Expected result of the test
Input data | Input data used to run the test
Priority | Criticality of the test case based on the priority of the User Story. A description of possible values can be found in the Settings sheet
Tester | Name or Alias of the person who performs the test
Date | Date the test is performed.
State | Drop-down list with the result of the test. The description for each possible state can be found in the Settings sheet
Test error comments | Description of the error, warning or blocking condition that prevents the test to succeed.
Id Jira | Jira Identifier of the task opened to solve the error detected in the testing
Regression
Detailed list of regression test cases. The columns in this section are the same as for the Epic sheets
Settings
Full list of values for Priority and State columns in the Epic and Regression sheets
Daily follow up
The first table provided in this sheet provides a summary of test results per Epic: - Percentage of passed tests and summary of test case results per State - Row "% TC per priority": Percentages of test cases per priority and summary of test case results per priority - Row "% TC Passed": Percentage of passed cases per priority - Row "% TC Pending": Percentage of test cases not tested per priority The second table provides the summary of test case results for all the epics implemented in current prototype.
Charts
This section provides the following 4 charts: 1. Total tests passed: Percentage of total test cases that are successfully passed, per priority. 2. Total tests not passed: Percentage of total test cases that are not successfully passed or tested, per priority. 3. Regression tests passed: Percentage of regression test cases that are successfully passed, per priority. 4. Regression test not passed: Percentage of regression test cases that are not successfully passed or tested, per priority. The legend at the bottom describes the color code used in the chart, which represent either the priority or the status of the test case.
Screen Shots
This section contains images or comments to support the execution of the test cases.
Add more Epic Name tabs
If more epics need to be added, the first table in the Daily follow up section should be extended with a new block for that epic. The formulas in both tables need to be updated accordingly. Steps to follow: 1. Copy Epic Name with one of the existing ones and change the name (Example: Epic Name 6) 2. On the Daily follow up sheet, select all the lines of an Epic Name block (Example: rows 2 to 6 belonging to Epic 1) and paste them at the end of last Epic Name 3. Formulas to be modified for each added Epic name: Those marked in red in the image, where the name of the epic Name of the formula will have to be modified by the new name that has been given to the sheet. It will also be necessary to modify the cells marked in green that calculate the means of the general% of all the Epic Names, adding the necessary cells in the formulas. Example: the Total passed test cases for the sprint is: = AVERAGE (C2; C7; C12; C17; C22) If another tab is added, we will need to add cell C27, thus updating the formula to = AVERAGE (C2; C7; C12; C17; C22; C27) Note: If a column is not going to be used (e.g. Tester, because the same person will do the testing), don't eliminate it, but hide it instead.
Remove more tabs from Epic Name
If it is necessary to eliminate tabs because we have less than 5 Epics. It will also be necessary to eliminate the necessary blocks in the daily follow up tab and modify the formulas so that it works correctly. Steps to follow: 1. Remove the tabs that we do not need (If we only need 3 Epics, delete Epic Name 4 and Epic Name 5). 2. On the Daily follow up tab, delete the last two blocks of Name Epic (it would be from row 17 to 26). Be careful not to eliminate the Regression block. 3. In the formulas of the means also have to eliminate the corresponding boxes marked in green in the following image: Example: the Total passed test cases for the sprint is: = AVERAGE (C2; C7; C12; C17; C22) --> C17 and C22 would have to be eliminated from the formula

## Settings
Priority | Description | Colour
1 - Critical | Blocking for the global process.
2 - High | Blocking for the functionality
3 - Medium | Not blocking. Workaround possible through tool interface
4 - Low | Specific cases, functionality not affected. User experience maybe affected.
State | Description | Colour
Passed | The test was successful
Failed | The test was wrong
Not Completed | It's unclear for the tester whether the result of the test is correct or not. The tester needs to contact the Product Owner and Solution Delivery Office to get further clarifications on the expected behaviour.
Blocked | The test is blocked waiting to be run
N/A | The test can not be performed

## Epic Name 1
EPIC: Name Epic
Environment: |  | Iteration:
Test Plan | [9 empty] | Validation Status
Id Test Case (US-SC-TC) | User Story | Scenario | Precondition | Test Case Description | Acceptance Criteria | Input data | Priority | Tester | Date | State | Test error comments | Id Jira

## Epic Name 2
EPIC: Name Epic
Environment: |  | Iteration:
Test Plan | [9 empty] | Validation Status
Id Test Case (US-SC-TC) | User Story | Scenario | Precondition | Test Case Description | Acceptance Criteria | Input data | Priority | Tester | Date | State | Test error comments | Id Jira

## Epic Name 3
EPIC: Name Epic
Environment: |  | Iteration:
Test Plan | [9 empty] | Validation Status
Id Test Case (US-SC-TC) | User Story | Scenario | Precondition | Test Case Description | Acceptance Criteria | Input data | Priority | Tester | Date | State | Test error comments | Id Jira

## Epic Name 4
EPIC: Name Epic
Environment: |  | Iteration:
Test Plan | [9 empty] | Validation Status
Id Test Case (US-SC-TC) | User Story | Scenario | Precondition | Test Case Description | Acceptance Criteria | Input data | Priority | Tester | Date | State | Test error comments | Id Jira

## Epic Name 5
EPIC: Name Epic
Environment: |  | Iteration:
Test Plan | [9 empty] | Validation Status
Id Test Case (US-SC-TC) | User Story | Scenario | Precondition | Test Case Description | Acceptance Criteria | Input data | Priority | Tester | Date | State | Test error comments | Id Jira

## Regression
EPIC: Name Epic
Environment: |  | Iteration:
Test Plan | [9 empty] | Validation Status
Id Test Case (US-SC-TC) | User Story | Scenario | Precondition | Test Case Description | Acceptance Criteria | Input data | Priority | Tester | Date | State | Test error comments | Id Jira

## Daily follow up
Date | Tested User Stories | % TCs Executed |  |  |  | Total test cases |  |  |  | Test cases Passed |  |  |  | Test cases Failed |  |  |  | Test cases Not Completed |  |  |  | Test cases Blocked |  |  |  | Test cases N/A |  |  |  | Not Tested |  |  |  | Comments
mm-dd | Epic Name 1 | 0% |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Priority | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L
| % TCs per priority | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| % TCs Passed | 0% | 0% | 0% | 0%
| % TCs Pending | 0% | 0% | 0% | 0%
mm-dd | Epic Name 2 | 0% |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Priority | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L
| % TCs per priority | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| % TCs Passed | 0% | 0% | 0% | 0%
| % TCs Pending | 0% | 0% | 0% | 0%
mm-dd | Epic Name 3 | 0% |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Priority | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L
| % TCs per priority | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| % TCs Passed | 0% | 0% | 0% | 0%
| % TCs Pending | 0% | 0% | 0% | 0%
mm-dd | Epic Name 4 | 0% |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Priority | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L
| % TCs per priority | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| % TCs Passed | 0% | 0% | 0% | 0%
| % TCs Pending | 0% | 0% | 0% | 0%
mm-dd | Epic Name 5 | 0% |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Priority | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L
| % TCs per priority | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| % TCs Passed | 0% | 0% | 0% | 0%
| % TCs Pending | 0% | 0% | 0% | 0%
mm-dd | Regression | 0% |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Priority | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L | C | H | M | L
| % TCs per priority | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| % TCs Passed | 0% | 0% | 0% | 0% | 0% | Total not Coverage R.
| % TCs Pending | 0% | 0% | 0% | 0% | 0% | Total Coverage R
| Total passed test cases for the sprint | 0% |  |  |  | 0% | 0% | 0% | 0% | Average of not passed test cases per priority for the sprint
| Average of passed test cases per priority for the sprint | 0% | 0% | 0% | 0% | 0% |  |  |  | Total not passed test cases for the sprint